## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US01 | As a developer, I want to design and implement the foundational database schema to store flight, booking, and passenger details. | MUST HAVE | Data structure design finalized, Database setup available. | Backend Team | 3- Completed
Sprint 1 | Sprint 1 | US02 | As a user, I want to search for flights using Origin, Destination, and Departure Date. | MUST HAVE | Flight dataset prepared, API endpoints for search ready | Backend Team | 3- Completed
Sprint 1 | Sprint 1 | US03 | As a system, I want to validate search inputs and return efficiently sorted search results. | SHOULD HAVE | Valid input schema defined, Core Backend API integration complete. | Backend Team | 3- Completed
Sprint 2 | Sprint 2 | US04 | As a system, I want to dynamically calculate flight prices based on real-time demand and time factors. | MUST HAVE | Pricing logic implemented, Access to real-time flight data. | Backend Team | 3- Completed
Sprint 2 | Sprint 2 | US05 | As a developer, I want to simulate demand shifts and fare history to test and refine the dynamic pricing algorithm. | COULD HAVE | Dynamic pricing algorithm stable, Demand simulation module available. | Backend Team | 3- Completed
Sprint 3 | Sprint 3 | US06 | As a user, I want to complete a booking and receive a unique Confirmation (PNR). | MUST HAVE | Booking API functional, Database integration for transactions ready. | Backend Team | 3- Completed
Sprint 3 | Sprint 3 | US07 | As a user, I want to view my booking history and request cancellation of an existing reservation. | SHOULD HAVE | Booking API functional, Database integration for history retrieval ready. | Backend Team | 3- Completed
Sprint 4 | Sprint 4 | US08 | As a user, I want a comprehensive and responsive frontend interface to search and book flights. | MUST HAVE | All Backend APIs (Search, Booking) ready for consumption. | Frontend Team | 3- Completed
Sprint 4 | Sprint 4 | US09 | As a user, I want to view a booking receipt/confirmation page after successful payment simulation. | SHOULD HAVE | Payment simulation module available, Full Frontend-backend integration. | Both Teams | 3- Completed
Note on F1: Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 95 | 17 | 17 | 16 | 20 | 10 | 6 | 6 | 2 | 1 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US01 | T01 | Design and implement flight database schema | 2025-09-04 | 2025-09-07 | Backend 1 | Design | 3- Completed | 8 | Day 1: 2; Day 2: 2; Day 3: 2; Day 4: 2
US02 | T02 | Create flight search API using FastAPI | 2025-09-08 | 2025-09-12 | Backend 2 | Coding | 3- Completed | 12 | Day 1: 1; Day 2: 3; Day 3: 2; Day 4: 3; Day 5: 3
US03 | T03 | Add validation and sorting logic in API | 2025-09-13 | 2025-09-17 | Backend 3 | Unit Test | 3- Completed | 8 | Day 1: 2; Day 2: 2; Day 3: 0; Day 4: 0; Day 5: 0; Day 6: 0; Day 7: 2; Day 8: 2
SPRINT 2 BACKLOG
US04 | T04 | Implement dynamic pricing logic | 2025-09-19 | 2025-09-25 | Backend 4 | Coding | 3- Completed | 10 | Day 1: 2; Day 2: 1; Day 3: 2; Day 4: 1; Day 5: 2; Day 6: 2
US05 | T05 | Simulate demand shifts and fare updates | 2025-09-26 | 2025-10-02 | Backend 5 | Build | 3- Completed | 12 | Day 1: 1; Day 2: 1; Day 3: 2; Day 4: 2; Day 5: 2; Day 6: 1; Day 7: 3
SPRINT 3 BACKLOG
US06 | T06 | Implement booking and payment process | 2025-10-03 | 2025-10-10 | Backend 5 | Integration Test | 3- Completed | 12 | Day 1: 2; Day 2: 2; Day 3: 3; Day 4: 5
US07 | T07 | Add cancellation and booking history | 2025-10-11 | 2025-10-16 | Backend 6 | System Test | 3- Completed | 8 | Day 1: 2; Day 2: 2; Day 3: 2; Day 4: 2
SPRINT 4 BACKLOG
US08 | T08 | Create frontend UI for flight search and booking | 2025-10-17 | 2025-10-25 | Frontend 1 | Design | 3- Completed | 15 | 3 | 2 | 2 | 3 | 2 | 1 | 1 | 0 | 1
US09 | T09 | Integrate backend APIs and generate receipts | 2025-10-26 | 2025-10-30 | Botht teams | Integration Test | 3- Completed | 10 | Day 1: 2; Day 2: 2; Day 3: 1; Day 4: 2; Day 5: 1; Day 6: 2; Day 7: 0
Note on D2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on E2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on I3: This is the total task estimated in hours for all the user stories
Note on J3: Pending effort hours after completion of day 1 work
Note on K3: Pending effort hours after completion of day 2 work
Note on L3: Pending effort hours after completion of day 3 work
Note on M3: Pending effort hours after completion of day 4 work
Note on N3: Pending effort hours after completion of day 5 work
Note on O3: Pending effort hours after completion of day 6 work
Note on P3: Pending effort hours after completion of day 7 work
Note on Q3: Pending effort hours after completion of day 8 work
Note on R3: Pending effort hours after completion of day 9 work
Note on S3: Pending effort hours after completion of day 10 work
Note on T3: Pending effort hours after completion of day 11 work
Note on U3: Pending effort hours after completion of day 12 work
Note on V3: Pending effort hours after completion of day 13 work
Note on W3: Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 3 | API response time was unexpectedly high during load testing of the search endpoint. | Optimized the most critical database queries to reduce latency.
Sprint 1 | Day 6 | Inconsistent input handling led to frequent validation errors in the search API. | Integrated Pydantic for rigorous input schema validation across all endpoints.
Sprint 2 | Day 5 | Dynamic price recalculation failed to trigger under specific traffic/time conditions. | Corrected the logical condition bug within the core pricing function.
Sprint 3 | Day 4 | Observed a race condition (concurrent update) during booking attempts. | Implemented database transaction locking to ensure atomicity and data integrity.
Sprint 4 | Day 2 | Frontend could not connect to the backend API due to CORS policy restrictions. | Updated and properly configured the FastAPI CORS middleware to allow UI access.
Sprint 4 | Day 8 | Final booking receipt displayed static data instead of dynamically retrieved details. | Adjusted the JSON response mapping logic between the backend service and frontend components.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2025-09-04 | 2025-09-18 | Backend Team | Write unit tests early | Skipping validation tests | Following coding standards | Added automated testing steps after API development
2 | Sprint 2 | 2025-09-19 | 2025-10-02 | Backend Team | Optimize queries | Complex logic without testing | Maintaining consistent API structure | Simplified dynamic pricing logic and improved documentation
3 | Sprint 3 | 2025-10-03 | 2025-10-16 | Frontend Team | Perform integration testing early | Testing after full development | Using DB transactions for concurrency | Added row-level locking in booking system
4 | Sprint 4 | 2025-10-17 | 2025-10-30 | Frontend Team | Perform UI-backend integration testing early | Leaving UI polising till last | Using structured daily stand-ups | Completed final UI testing and fixed API response issues