## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | QA Team | 2025-10-25 | Search results show 'No flights found' even when flights exist | Sprint 2 | Backend Team 2 | Logical | Corrected SQL filter & added test cases | 2025-10-26 | Closed | Verified, working fine
2 | QA Team | 2025-10-26 | Text not visible due to light theme contrast issue | Sprint 2 | Frontend Team 1 | User Interface | Adjusted colors & added accessibility contrast check | 2025-10-27 | Closed | Issue resolved
3 | QA Team | 2025-10-27 | Payment endpoint returns 422 for valid request | Sprint 3 | Backend Team 1 | Logical | Updated validation schema | 2025-10-28 | Closed | Functionality verified
4 | QA Team | 2025-10-28 | Flight results load slowly on low bandwidth | Sprint 4 | Backend Team 1 | Maintainability | Implemented lazy loading & response compression | 2025-10-29 | Closed | Performance improved